## Slide 1: USAID Rulemaking Timeline (starting with a proposed rule requiring a public comment period)
Proposed Rule Planning Stage
OMB Review of Proposed Rule
(90 Days)
Once OMB/OIRA finishes their significance review, the CFR Owner sends the proposed rule and an action memo that contains all the required information per ADS 156 (clearances, cost analysis, correct format, etc.) to the Regulatory Policy Officer (RPO).
Once the RPO approves the rule for publication, the CFR Owner works with the USAID Federal Register liaison to publish the rule.
Publication of Proposed Rule
M/MPBP/POL sends the rule to OMB/OIRA for their significance review under E.O. 12866.
OMB/OIRA determines whether the rule is significant.
If OMB/OIRA determined the rule is significant, the CFR owner and IPO prepare a Regulatory Analysis (RA). If it is not significant, then this step can be skipped. (See ADS 156 for the RA guidance)
The OMB/OIRA review can take up to 90 days.
Once the rule has been published, the public has up to 60 days to provide comments.
M/MPBP/POL will set up the FDMS docket.
M/MPBP/POL advises the CFR Owner of the FDMS docket number and how to use the FDMS system to monitor and retrieve public comments. The CFR owner can also use regulations.gov to see how many comments there are (note: this only shows the number not the actual comments).
Public Comments
(60 Days)
Preparation of Final Rule
Publication of Final Rule
(Rule becomes Effective within 30 Days)
The CFR Owner, IPO, and GC review and answer comments.
If the final rule is significant, the CFR Owner and M/MPBP/POL coordinate with OMB/OIRA to address any controversial/ significant comments for draft of final rule. OIRA has 90 days to review.
The CFR Owner and IPO draft the final rule. The CFR Owner sends the final rule and an action memo to the RPO to authorize publication of the final rule in the Federal Register.
register and the public has an
The CFR Owner coordinates with the USAID Federal Register liaison to publish the final rule (same internal process as the proposed rule).
M/MPBP/POL fills out and submits the Congressional Review Act (CRA) form and the FR notice (FR notices can be found here: federalregister.gov) to LPA.
The final rule becomes effective 30 days after its publication in the Federal Register, unless it is a major rule (60 days). The CRA form must be submitted to Congress before the rule can become effective.
The Code of Federal Regulations (CFR) Owner (in consultation with the Initiating Program Office (IPO) contacts M/MPBP/POL to inform of their intent to publish a rule.
M/MPBP/POL provides guidance to the CFR Owner regarding the notice of proposed rulemaking (NPRM) and overall rulemaking process.
M/MPBP/POL includes the proposed rule in the Spring or Fall Unified Agenda.
CFR Owner/IPO circulates a draft proposed rule for internal review/comment to GC and stakeholder offices.

## Slide 2: USAID Rulemaking Timeline (for rules that don’t require public comment)
Proposed Rule Stage
The Initiating Program Office (IPO)/ CFR Owner contacts M/MPBP/POL to inform of their intent to publish a rule.
M/MPBP/POL provides guidance to IPO/ CFR Owner regarding the interim final/direct final rule and overall rulemaking process.
M/MPBP/POL includes the final/direct final rule in the Spring or Fall Unified Agenda
The rule must include an analysis of why public comments were deemed unnecessary. OMB/OIRA will review the analysis and determine whether or not an NPRM (including comments) is required.
OMB Review of Proposed Rule
(90 Days)
Once OMB/OIRA finishes their significance review, the IPO sends an action memo to the Regulatory Policy Officer (RPO) to authorize publication of the interim/direct rule in the Federal Register (see ADS 156.3.2.5b regarding the good cause exception, if applicable).
M/MPBP/POL ensures the memo contains all the required information per ADS 156, Agency Rulemaking (clearances, cost analysis, correct format, etc.).
Once the RPO approves the rule for publication, the IPO works with the USAID Federal Register liaison to publish the rule.
Preparation of Interim Final/Direct Final Rule
M/MPBP/POL sends the rule to OMB/OIRA for their significance review under E.O. 12866.
OMB/OIRA determines whether the rule is significant. If the rule is significant, the NPRM will be required unless the "good cause" exception applies (refer to the other timeline for next steps if the rule requires an NPRM).
This review can take up to 90 days.
Publication of Interim/ Direct Final Rule
The IPO coordinates with the USAID Federal Register liaison to publish the final rule.
M/MPBP/POL fills out and submits the Congressional Review Act (CRA) form and the FR notification (can be found here: federalregister.gov) and sends it to LPA.
The rule goes into effect immediately unless an adverse comment comes up. For a direct final rule, the Agency will withdraw the rule, revise and submit a NPRM. For an interim rule, the Agency will make edits to the final rule and resubmit it.
gisthe public has an